## Sheet1
Diamond radiator fabrication and assessment
radiator lifetime | 200 | hr | conservative estimate 1 C/cm^2 at center at 10^8 g/s intensity
run time / year | 2592 | hr | based on 120 days at 90% efficiency
diamonds / year | 13
costed run time | 1.2 | yr | sized to cover 2 years at 10^7 g/s and a third year at 10^8 g/s
total diamonds | 16
cost of raw stone | 2340 | US$ | 6x6x1.2 mm^3 single-crystal CVD plate (E6 online listed price)
total for stones | 37440 | US$
(initial thickness of raw stones too large, etch down to 300um)
etch cost per stone | 1000 | US$ | conservative estimate, based on conversation with Sinmat
laser cost per stone | 1000 | US$ | supplies for laser, cleaning operations, basis actual costs in 2012
total materials | 69440 | US$
Zygo imaging | 5 | hr/stone | before between ablation cycles, before and after cleaning cycles
ablation setup | 8 | hr/stone | clean and align optics, find spot focus, generate mill program
actual ablation | 30 | hr/stone | sufficient time to mill slowly during the final passes
cleaning | 10 | hr/stone | several cycles of ozone cleaning and acetone untrasound
X-ray imaging | 30 | hr/stone | includes time to set up at beam line, take data, analyze data
labor rate | 45 | US$/hr | effective rate for graduate student assistantship
total labor hours | 1328 | hr
total labor cost | 59760 | US$
total diamonds cost | 129200 | US$
Diamond target mount assembly
design labor | 80 | hr | aluminum disk with cut-outs for diamonds and mounting fingers
prototyping labor | 80 | hr | build a single-window prototype for testing at CHESS
final design labor | 40 | hr | finalize design based on experience with prototype
final machining | 80 | hr | actually machine the final part
designer/tech rate | 45 | US$/hr | effective rate for graduate student assistantship
machining rate | 45 | US$/hr
total labor cost | 12600 | US$
parts + materials | 3000 | US$
total mount cost | 15600 | US$