## Slide 1: Tagger Magnet Procurement Schedule
Jim Stewart
Internal Review
July 2009

## Slide 2: Tagger magnet design
1.5 T nominal field
1.1 m wide 1.4 m high 6.3 m long
Slabbed construction
Heaviest piece < 25 t
12 GeV e- bent 13.4 °
Electron measurement
  30 mm pole gap
  9 – 0.3 GeV electrons
  11.7 to 3 GeV photons
  ~0.04% E/E0 intrinsic resolution!

## Slide 3: Design Status Summary
Initial 3-D models exist but they are not final.
  Changes still being made.
No real assembly or detail drawings exist.
Original FEA analysis has been done at Glasgow.
Substantial FEA analysis is being done now @ JLAB.
Need jacks to separate iron plates

## Slide 4: Procurement possible Strategies
Issue a design and build contract
  Here the company will be given our reference design and then finish the design or start from scratch.
Finish the design and then issue a set of build contracts.
  Here we have to generate all documentation and shop drawings ourselves.
  Design could be done by an additional contract.

## Slide 5: Design and build contract
JLAB will define the specification and the statement of work for the magnet and the vacuum chamber.
  Will include a drawing set and the specification which represents the reference design.
Companies bid on the magnet with a proposal how it will be built.
  They can change the design as long as meets our requirements.
  They are required to provide all analysis.
When the final design is finished it will be reviewed.
Material procurement and manufacturing starts.

## Slide 6: Build contract
JLAB will design all the components of the magnet system.
  Magnet Yoke
  Magnet Coils
  Stands
  Vacuum chamber
We produce all final drawings with tolerances.
We provide the exact specifications for all materials, handling, and quality control.
We produce all safety related analysis and documentation.

## Slide 7: Pros and Cons
 | Design and Build | Build
Design Effort | We don’t have to finish the design. Must review their design. | Must finish our design.
Procurement Effort | 1 contracting company | Possibly 4 separate contracts.
Cost | Must pay for all design work and testing at the company (+profit). Must integrate their documents into JLAB | Must pay to finish the design. Must produce full documentation set.
Risk | Can benefit from outside experience. Company accepts responsibility for mistakes. Additional optimization may save cost. | If we make a mistake we will need to fix it. (How to evaluate risk?)
Q&A | Will test/map the magnet at the company. | We must assure Q&A.

## Slide 8: Results from RFI issued 1 year ago concerning feasibility and cost
Companies claiming to be able to build
Babcock Noell GmbH
Bruker Biospin
Everson Tesla
General Atomics
Milhous Company
Precision Custom Components
Sigmaphi
Cost Estimate for the magnet only
  3 estimates
  $500-950k
Note: The dollar-euro rate and steel prices have changed in the last year.

## Slide 9: RFQ 2 years ago for magnet design
Typical costs $250k-$370k
Total cost range $100k to $700k

## Slide 10: SigmaPhi
Tim met with the a rep. from SigmaPhi in May 09 to discuss the magnet.
If it is a design and build they would start from scratch as they will be responsible. Plan for 2 years between issuing the contract and delivery. Cost ~$1.2M for the magnet only. They can map if we request.
No vacuum chamber or stand

## Slide 11: Design and Build contract timeline
Post RFQ Jan 2010
Receive Quotes
March 2010
Place Order
June 2010
Receive Design
Jan 2011
Approve Design
Feb 2110
Iron and Cu Available
July 2011
Manufacturing Complete
July 2012
Acceptance Test Aug 2012
Delivery JLAB
Sept 2012
Test Magnet
Study Hysteresis
Excitation Curve
Fine mesh Map
Install Detectors
~6 mo
Float

## Slide 12: Build Only Schedule
Post RFQs July 2010
Receive Quotes
Oct. 2010
Place Orders
Jan 2011
Iron and Cu Available
July 2011
Manufacturing Complete
June 2012
Magnet Delivery
July 2012

## Slide 13: Effort for Design and Build
Now to RFQ | 5 mw Engineer | Finish SOW and PR.
 | 7 mw Designer | Finish drawing package for bid.
Review Bids | 6 mw Engineer | 3 mw answer questions from companies. 31 wk committee reviews bids .
Design phase support | 3 mw engineer | Reviews at 1.5 mo and 6 mo. Check design and documents.
 | 2 mw designer | Support for design review.
Build phase | 4 mw engineer | Site visits. Testing review.
Delivery | 4 mw | Documentation and Safety integration.
Total : 22mw Eng. 9 mw Designer (~$85k)

## Slide 14: Effort for a build only contract
Now to RFQ | 14 mw Engineer | Finish FEA. Documentation. Safety analysis.
 | 32 mw Designer | Finalize design. Make all drawings. Get signed archived drawings.
Review Bids | 6 mw Engineer | Review 4 different contracts.
Build phase | 4 mw engineer | Site visits. Testing review.
Delivery | 3 mw | Certificates Documentation and Safety review.
Total : 27 mw Eng. 32 mw Designer (~$148k)

## Slide 15: Overview of what is in P3E for the tagger magnet excluding installation
Activity Activity Start Finish Bud. Labor Bud.Labor Bud. Mat. Bud. Total
ID Name Cost Cost Cost Cost
15511005 Drawings for Yoke Steel 01-Apr-10 20-Sep-10 43.0w $41,676 $0 $41,676
15511010 Drawings for Coils 01-Apr-10 20-Aug-10 65.0w $52,966 $0 $52,966
15511015 Drawings for Vac Chamb 01-Apr-10 20-Sep-10 65.0w $52,966 $0 $52,966
15511025 Dsgn Stands for Mag 01-Apr-10 24-Jun-10 37.0w $41,676 $0 $41,676
15511030 Dsgn Supprt for Vac Chamb 01-Apr-10 03-Sep-10 37.0w $41,676 $0 $41,676
15511040 Write Pwr Supply Spec 23-Aug-10 27-Sep-10 11.0w $6,938 $0 $6,938
15511045 EH&S Review of Dsgn 21-Sep-10 27-Sep-10 0.0w $0 $0 $0
15511050 Proc Yoke Steel 05-Jan-11 26-Aug-11 2.0w $1,334 $541,992 $543,326
15511060 Proc Vac Chamb 05-Jan-11 30-Mar-11 3.0w $2,000 $70,948 $72,948
15511065 Proc Pwr Supply 05-Jan-11 31-Mar-11 0.0w $0 $64,735 $64,735
15511105 Tag Mag Acceptance Test 02-Jul-12 02-Jul-12 0.0w $0 $0 $0
15511110 Shipping to JLab 03-Jul-12 27-Aug-12 0.0w $0 $34,074 $34,074
Power Supply Subtotal 11.0w $6,938 $64,735 $71,673
Tagger Dipole Subtotal 252w $234.3k $647k $881.3

## Slide 16: Budgeted cost for installation
Activity ID Activity Name Start Finish Bud. Labor Bud. Material Bud. Total
1562045 Install Tagger Magnets & Chamber 28-Aug-12 30-Oct-12 04:00 PM $26,035 $27,685 $53,720
1562050 Install Tagger Pwr Supply (Installtn) 27-Jun-12 24-Jul-12 04:00 PM $17,612 $10,648 $28,261
1562055 Install LCW Connections (Installtn) 25-Jul-12 21-Aug-12 04:00 PM $9,248 $2,130 $11,378
1562060 Survey & Align Magnets (Installtn) 31-Oct-12 13-Nov-12 04:00 PM $16,090 $0 $16,090
1562061 Field Map Tagging Magnet 14-Nov-12 19-Feb-13 04:00 PM $22,581 $0 $22,581
Total $91.5k $40.5k $132k
Remember this includes: Magnet Survey, Magnet Assembly, Power Supply Installation, Cables, Cable Trays, Water, Temperature Switches, Controls, Programming Controls, Testing the Magnet, Hysteresis Suppression Studies, Generation of the excitation table for CEBAF, Mapping the Magnet, A Mapping Machine if needed including software ….
Summary: 2 technician man years of effort and $40k material

## Slide 17: Must decide on the best plan!
Main Factors to consider:
  Is expert manpower available in house?
    Expertise in the Hall-D group is lacking.
  How large is the risk in finishing the magnet design ourselves?
If expert manpower can be found in house then the magnet should be built at budget.

## Slide 18: Backup

## Slide 19: Pros and Cons
Design and Build
Pros
  Do not need to finish the design.
  Can benefit from company’s experience .
  Company will generate the necessary documentation.
  Company can test the magnet before delivery.
    Know we will receive a working magnet!
Cons
  Must review the company’s proposal.
  Must pay for all design work at the company.
Straight Build
Pros
  Do not have to review the company’s final design.
  Cost of contracts may be less as the companies do not need to engineer.
Cons
  Cannot benefit from company’s experience.
  More work in procurement here due to multiple contracts.
  Q&A is more important as only partial testing can be done before delivery.
  First assembly and testing at JLAB.

## Slide 20: Manpower cost
Mech Eng $63.81 per hr
  63.81*40*(52/44)= $3.0 k per mw
    Fully burdened non-escalated effort
  Mech Designer $43.84 per hour
  $43.84 *40*(52/44)=$2.1 k per mw
    Fully burdened non-escalated effort

## Slide 21: Overview
11.1 m long
Exit Window
1” reinforcing ribs.
¼” Stn.Stl. Shell
  Max 1 mm deflection
3/8” (9.5 mm) O-ring
Brackets to support vacuum forces.
Two NMR probes for field stabilization and monitoring.