## Slide 1
Are the magnetic, mechanical and electrical requirements for the tagger magnet adequately defined?
  Findings/Comments
    Spectrometer resolution requirements are well stated
    Global field uniformity specification is ambiguous and potentially in error
    Magnetic field specifications are incomplete
    Magnetic, Mechanical and Electrical requirements are stated, but not justified…rational behind them is unclear
  Recommendations
    Conduct a full resolution error analysis
    Use these results to improve the magnetic field specifications
    Use improved magnetic field specifications to update mechanical requirements
    Consider spectrometer calibration technique to verify performance

## Slide 2
Is the reference design adequately defined at this point in time to address all requirements?
  Findings/Comments
    The design has addressed the requirements as stated
    The design seems to have adequately anticipated a variety of problems
  Recommendations
    Update as needed after completing the recommendations from Charge #1

## Slide 3
Is the reference design adequately developed to justify completing the design in-house or should the final design be sub-contracted to an external source?
  Findings/Comments
    The reference design is well advanced and adequately developed to justify completing the design in-house
  Recommendations
    Complete the design in-house

## Slide 4
Is the procurement schedule and plan reasonable? Is it reasonable to assume that the complete package can be sub-contracted to one company? Should the procurements be broken up?
  Findings/Comments
    Plans for Design-and-build as well as Build-to-print were presented
    Procurement schedules and plans are reasonable
    Concurrent design and fabrication appear to be a way to gain float in the schedule and helps with resource leveling
    There are companies that have the capabilities to do the complete scope (design and build)
    Engineering resources for contract award and management appear low
  Recommendations
    The costs presented need to be updated to reflect the current market condition and design completeness
    Recommend multiple build-to-print procurements

## Slide 5
Have ES&H considerations been adequately incorporated into the in-hall installation plans and the design at their present stage?
  Findings/Comments
    ES&H considerations have been adequately addressed to the design level at their present stage
    Pressure safety for the vacuum chamber design has been thoroughly addressed by using ASME BPV
    Installation plans at the current design level have been done with prudence regarding ES&H guidance
    Recent addition of an experienced hall coordinator will greatly enhance the work planning and scheduling
  Recommendations
    Continue with the development of the procedures, lift plans, pertinent OSPs and TOSPs, etc.